## Sheet1
Project Status Check Report Team - 1
Sl no. | Employee ID | Name | Domain | Module | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2022-12-14
1 | 2576365 | Subashini Ravi | Testing | Add-To-cart | Started implementation with TestNG | In progress with finding the Xpath of Add-To-cart | In progress with doing the manual implementation of Add-To-cart | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
2 | 2576394 | Swetha Andrews | Testing | Login | Started implementation with TestNG | In progress with finding the Xpath of Login | In progress with tdoing the manual implementation of Login | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
3 | 2576252 | Himadri Shekhar Ghosh | Testing | My Profile | Started implementation with TestNG | In progress with finding the Xpath of My Profile | In progress with doing the manual implementationof My Profile | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
4 | 2576622 | Bollu Haritha | Testing | Cart | Started implementation with TestNG | In progress with finding the Xpath of cart | In progress with doing the manual implementation of cart | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
5 | 2577073 | Gurram Pratyusha | Testing | Search | Started implementation with TestNG | In progress with finding the Xpath of Search | In progress with doing the manual implementation of Search | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
6 | 2576240 | Boligarla Keerthi | Testing | ShortList | Started implementation with TestNG | In progress with finding the Xpath of Shorlist | In progress with doing the manual implementation of Shorlist | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
7 | 2576900 | Shubhendu Shekhar | Testing | Presschool Locator | Started implementation with TestNG | In progress with finding the Xpath of Presschool Locator | In progress with doing the manual implementation of Presschool Locator | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
8 | 2576429 | Papana Ratnapradeep Reddy | Testing | Store Locator | Started implementation with TestNG | In progress with finding the Xpath of Store Locator | In progress with doing the manual implementation of Store Locator | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving
9 | 2576333 | Diksha Prasad | Testing | My Profile | Started implementation with TestNG | In progress with finding the Xpath of My Profile | In progress with doing the manual implementation of My Profile | Done the TestNg Implementation od code | started implementation with cucumber | completed cucumber implementation | Integeration of the project | Error solving